## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Since i highly prefer the markdown editor on Github, i provided a more detail description there.
Basic setup | 3 | 2024-01-02 | creation of first assets: CellCube, SpawnController, Materials
MazeGenerator: creation of Cell assets, started to write the algorithm | 2.5 | 2024-01-04 | created Cell & CubeCell scripts. I wanted to add triangle & hexagon mazes later on, thats why i built it this way. I decided to use the backtracking algorithm since i liked the gif on the website and started the implementation of it. I choose a recursive way, as it was explained like that on the wikipedia page.
Housekeeping | 1 | 2024-01-13 | Here comes the fun part, since i havent worked on the Assessment for a few days i have checked my repository and realized that the gitignore file didnt ignore the files it shouldve ignored, so i deleted them locally because i believed it would be faster than doing it in the repo. Afterwards i had a memory allocation error, sadly any fix i searched for didnt help, so i decided to start over.
Restart from Scratch: Generation Algorithm | 3 | 2024-01-14 | I restarted with a fresh project and recreated everything i had before. Funnily i was faster and everything worked. The Generation algorithm was finished with a few selectable options like width and height of the maze as serializeFields.
beginning of the UI | 2 | 2024-01-14 | Creation of UI Elements and the UI manager script.
UI refinement, script, and communication between scripts | 2.5 | 2024-01-15 | Here i wrote all methods to interact with the UI and the interaction with the generation script. I also refined the UI elements
rewrote Algorithm, new UI functionality | 1 | 2024-01-15 | As i tested the generation algorithm with the UI i realized that selecting a size of 250x250 triggers a stack overflow, so i had to rewrite the algorithm into an iterative version. I also added a slider for the camera distance and locking the size worked at this point.
Camera Movement, UI responsiveness | 0.5 | 2024-01-15 | The camera could now be moved with the WASD buttons, i worked on the responsiveness of the UI, i also reordered all files so its a bit more ordered. | 1
Final merge & Build | 0.5 | 2024-01-15 | I merged everything and built the application. I also made some final adjustments, e. g. The application can now be quit with the ESC button.
Total amount of hours | 10